## Sheet1
Description | Who? | 2020-06-04 | 2020-06-07 | 2020-06-10 | 2020-06-13 | 2020-06-16 | 2020-06-19 | 2020-06-22 | 2020-06-24 | Extended description
We have meetings Monday, Tuesday, Wednesday and Thursday at 20:00 at Friday, Saturday and Sunday at 10:00. Problems that require help should be mentioned before the meeting and help will be given outside of the meetings.
MAJOR BUILDS / MILESTONES
Report skeleton | René | [8 empty] | The basic structure of the report is finished
Finished report | René and Jean | [8 empty] | The report is completely finished
Random error in intitial position and velocity | Matthijs | [8 empty] | Introduce a small random error in the initial position and velocity of the ball and investigate how this affects performance of your bot. Vary the magnitude of this error, and investigate how your bot can find strategies to deal with it
Different coefficients of friction | Ivan | [8 empty] | Different greens have different coefficients of friction. Extend your bot to handle an unknown coefficient of friction (which you can try to estimate).
Flying and bouncing balls (including accordingly improved bot) | Matthijs, Aaron, Ivan | [8 empty] | If a ball is hit hard on a sloping course, it may fly into the air. Extend your simulator to handle flying and bouncing balls. You could even design some “crazy golf” courses.
Collision detection | Aaron | [8 empty] | Allow obstacles and bodies of water in your course design. Implement a collisiondetector for determining whether the ball has fallen into a body of water or hit an obstacle, and handle these appropriately.
Extended bot for maze-like courses (including test courses) | Ivan | [8 empty] | Extend your AI bot player to handle complex maze-like courses with obstacles. Design and test your bot on courses which allow you to identify the limits of your bots capabilities.
Report
The skeleton of the report (keywords and structures) | René | [8 empty] | Create the basics of the report in LaTeX (keywords and structures)
Report draft | René and Jean | [8 empty] | Have a rough version of the report to be checked.
Full report | René and Jean
title page | René
contents | René
list of tables and images | René
summary/abstract | René and Jean | [8 empty] | Motivation, problem statement, approach, main results, conclusion
intro | René and Jean | [8 empty] | Context, motivation, primary question, relevance, state-of-the-art, choice of focus, main approach, report structure
preliminaries | René and Jean | [8 empty] | Detailed and technical background
methodology | René and Jean | [8 empty] | Describe approach step by step, used algorithms, referring to originals works, description of used data
implementation | René and Jean | [8 empty] | Software implementation of the methods, UML diagrams, pseudocode
experiments | René and Jean | [8 empty] | Complete description of experiments/analysessimulations, including motivation and their uses.
results | René and Jean | [8 empty] | Results of experiments (without interpretation). Use tables and figures (including title and description of content)
discussion | René and Jean | [8 empty] | Interpret results, answer research questions, why are these the results, use previous studies as backup, how does this advance the state-of-the-art. Discuss issues and possible solutions. What are limitations of the study? How to continue on this work?
conclusions | René and Jean | [8 empty] | Summary of the study, answers to questions (no new info). How to continue with this research? Recommendations?
references | René | [8 empty] | used references
appendices | René | [8 empty] | appendices
Bot
Design improved bot | Ivan | [8 empty] | Design the improve bot that can handle maze-like structures, flying balls, water, trees and a random error in starting conditions
Basic version | Ivan | [8 empty] | Have a working version of the bot, but it doesn't have to be optimal
Improved bot finished | Ivan | [8 empty] | Have an optimal version of the bot working, including demonstrations of it working
Physics
Random error in initial position and velocity | Matthijs | [8 empty] | Add a random offset to the initial position and velocity of the ball
Flying balls | Matthijs | [8 empty] | Allow for the ball to fly instead of it being locked to the height of the terrain
Bouncing balls | Matthijs and Aaron | [8 empty] | Add physics for bouncing balls, this is meant for bouncing against trees and the terrain
Engine
Collision detection | Aaron (with René helping) | [8 empty] | Add collision detection to the ball so it can 'hit' trees and the water
Game mechanic
Reset ball after hitting the water | René and Jean | [8 empty] | Allow the user to select a point along the starting position up to the location where the water was hit using a UI.
Detect if you're on sand or on grass | René and Ivan | [8 empty] | Have a function that returns wheter you are on grass or sand
Presentation
Presentation | Aaron | [8 empty] | Create the presentation and practise
Planned duration
Finished earlier than planned
Critically behind on schedule
Possible extension
Disaster
Have something ready, even tough it's not optimal
Slightly behind
Requires extra attention